## Requirements
Sno | Form | Descriptions | Status | Priority
1 | Receipt | Add email address | Completed
2 | Customer Master | Remove GST mandatory | Completed
3 | Common - Barcode printers | Require configuration | Completed
4 | Physical Verification | Add NA in all conditions | Completed
5 | Auto hide side menu - to generate content space |  | Completed
6 | RID Print | Instead of "End Customer" show as "Customer" | Completed
7 | Receipt Close msg | Require to show correct RC id. | Completed
8 | RMA form | "Please enter GS number" Msg not required | Completed
9 | RMA creation form | No warranty selection is required | Completed
10 | Site displaying customer names |  | Completed
11 | Clicking outside removes the entire form |  | Completed
12 | RMA form | Invoice address to copied from delivery address and both address to be editable. | Completed
13 | RMA form | GS number, ACT number not mandatory | Completed
14 | RID, RMA print | Print success msg to be displayed and error msg if any. | Completed
15 | Edit, add, update options to be added to front of every line items |  | Completed
16 | Job ticket | After saving, it remains in open not moving to started. | Completed
17 | Job ticket | Print dialog to be appeared while selecting Print option | Completed
18 | Job ticket | Shall be completed without any material | Completed
19 | Job ticket | Repair comment mandatory | Completed
20 | Aging | "Aging Modal" haeding to be changed to "Aging Results" | Completed
21 | "Close" buttons to be changed to "Cancel" |  | Completed
22 | Verification Form | Relay received with screw, TB, case, battery, flops should be auto updated from Physical verification | Completed
23 | Dispatch form | Multiple RID selection - to create a single dispatch | Completed
24 | Dispatch form | By courier, By hand radio buttons with Courier name, Docket number and Person name, concern name and contact details respectively | Completed
| RMA form | Remove GST mandatory | Completed
| Dispatch form | Add mandatory GST field | Completed
25 | Receipt label | Change font size based on characters | Completed | 2
26 | Receipt form | Show customer name, Location in dropdown | Changed
27 | Receipt form | Rename Site to Location | Changed
28 | RID Label | Customer and Location dynamic font size | Completed | 2
29 | PV Font | Print pv form while creating new PV with RMA No | Completed
30 | Mail | Mail is not working | Working
31 | Landing Page | Change landing page to Receipt page | Changed
32 | W/C Page | Show relay received fields in W/C form | Changes not needed
33 | W/C Page | RCA mail flow | Completed
34 | Priority | priority flow to be discuss
35 | Dashboard | 1.Repair Priority, 2.Test, 3.Pack | Completed
36 | Dashboard | Gradient update | Completed
37 | Mail | EOD Mail to be discuss
38 | Notification Bubble | To be discuss
1 | W/CH approval form | PO kept mandatory at the initial stage. Mandatory To be removed | Resolved
2 | Email at W/CH declaration | 1.repaired / Modified on <> status empty(it is based on PCP field) 2. Defect reported by customer picking wrong value(map to desc_of_fault field in rma_unit_information table) | Resolved
3 | Query report | Error screen - sr. 34567419/09/18 | Resolved
4 | Job ticket | Warranty/ CH/ SMP-ch Status not known(if both are same show the value, if anything is chargable show the Chargable field eg. SMP-CH, PCP-CH), Physicalverificaiton comment, PV Received with fields to be shown as checkbox,. | Updated
5 | Job ticket
6 | PV form | Serial no cut due to larger model numbers
7 | PV form | Location and RID is required(Location from Receipt) | Updated
8 | Job ticket | RID in All forms (Job ticket, PV etc,), W/CH status | Updated
9 | Job ticket | Sofware Refereence not avaialble, to be added/ editable | Updated
10 | Job ticket | General Repair comment not availble in print | Resolved
11 | Job ticket | Job ticket print allignment | completed
12 | Verification completion | Output contact tests repaeated twice - 1 to be removed | Resolved
13 | Verification completion | Pass, fail, NA | Resolved
1 | Relay stage report | Include PV print form and Job ticket print form. | Completed
3 | Customer Master | Include Delete cutomer
4 | Job ticket print form | Change font size for tables | Changed
|  | donot exceed 2 pages | Resolved
|  | Footer misplaced | Resolved
|  | Taken date to be changed to jobticked started date | Updated
5 | W/CH | Rename Customer Comment to Defect by customer | Updated
6 | Job Ticket | Sub Category for type of work |  | 6
|  | Comment to be filled in the Remark field | Updated
7 | Job ticket print form | add Software reference in print form | Updated
|  | Maximum 8 row in a table | Updated
8 | Reports | From date to date in all reports | Added
|  | Add date field in grid | Added
1 | Job ticket print form | Remarks exceeds the border | Resolved
2 | Other relay status | Flow to be discuss
1 | Dashboard | product family change | Changed
2 | PV | product family change | Changed
|  | Add Delete PV option | Added
3 | Job Ticket | Add materials to be available even after completion | completed
|  | Show Warranty/CH in job ticket print form | Added
|  | Old PCB, New PCB Component table modification in print form |  | 7
|  | Old PCB, New PCB Characters length change | Updated
4 | Reports | Add date field in grid | Added
|  | add from date, to date in filters | Added
5 | Testing | Add Not required radio buttons in form | Completed
6 | Aging | Add Not required radio buttons in form | Completed
7 | One time data import
8 | W/Ch Flow |  | Changed
9 | Other relays flow |  | To be discuss
10 | Phone Qr code scanner |  | Completed
11 | Allow Manger to change W/Ch status until jobticket stage |  | Completed
12 | W/Ch | Mail addition,editable | Completed
| Dashboard | Show Current stage of relay on hovering serial no |  | 1 | Completed
|  | Increase blink time of overdues number |  | 1 | Completed
|  | Reduce carosel speed |  | 1 | Completed
|  | Remove "BOJ" from priority list |  | 1 | Completed
|  | Open and Started receipt to be shown. |  | 1 | Completed
|  | Rename Repair Priority to Customer Priority |  | 1 | Completed
|  | Rename Repair to Repair Priority |  | 1 | Completed
|  | Order->1.Repair Priority, 2.Repair,Test |  | 1 | Completed
|  | Update in charts |  | 1 | Completed
|  | Include Job Ticket stage in Repair Tab. |  | 3 | Completed
| Job Ticket | Dont show data in Open tab until user search. |  | 3 | Completed
|  | Nature of defect flow from RMA form. |  | 5 | Completed
| PV Print form | Show date in PV print form |  | 4 | Completed
|  | Increase font size in table |  | 4 | Increased upto max
|  | Excel export of all grid |  | 4
|  | Stored result (Yes/No) in Test report |  | 4 | Completed
|  | Don’t expiry the session |  | 4 | Completed
|  | Changes in Dispatch mail content |  | 4 | Completed
| RMA | Sitecard RMA Relays not listing in W/Ch | Completed
| Dashboard | W/Ch Overdue is Mismatching
2020-03-05
| Dashboard | Total realay in heading (Repair Priority) |  |  | Completed
|  | Add Repair table at end.(From JT to Test data) | To discuss
|  | Remove status tab and add overdue in Receipt table. | To discuss
Daily Save DB to Local Path
2020-03-09
Grid Export
|  | Admin,Mngr JT Grid Access |  | Completed
|  | Font Changes PV Print Form |  | Completed
|  | Dashboard Receipt Overdue |  | Completed
|  | Dashboard W/Ch Overdue Changes |  | Completed
Site Card Old RMA Entry
|  | Dashboard Overdue based on Category |  | Completed
Mail Changes
Repair Excel Report
Daily Report
|  | JT- Downloaded Customer Setting Field(Yes/No) |  | Completed
|  | JT-Print 12 rows |  | Completed
|  | VC-Restored Customer Setting Field(Yes/No) |  | Completed
Dispatch Approval/ Dispatch Functionality Interchange
|  | Daily DB Backup |  | Completed
Onetime upload
|  | Dashboard- Hover Over Overdue | (RID, Family, S.No, Overdue Age, Overall the overdue) | Completed
|  | Master - Overdue for individual Product Category |  | Completed
13/03/2020
| Mail Changes | In all Emails - Text “If you need further assistance, please contact CRC Hotline “ should changed to “If you need further assistance, please reply” |  | Completed
|  | Receipt Email Subject should be “Receipt Completion - < Receipt Id>” |  | Completed
|  | Physical Verification Email Subject should be “Physical Verification Completion – RMA: < RMA no>” |  | Completed
|  | W/C Declaration Email Subject should be “W/C Declaration – RID: < RID no>” |  | Completed
|  | Dispatch Email Subject should be “Dispatch Completion – RMA: < RMA no>” |  | Completed

## User Permission
User types | Access | View | Edit | Delete | Status
Admin | All | Y | All | Y | Completed
Manager | All | Y | (Masters Approval Outbound) | Y | Completed
Technician | All | Y | Excluding (Approval) | Nil | Completed

## EMail
Sno | Process | Content | Status | Email | From ID | User ID/PSw | To | Status
1 | Receipt | Email has to be sent on completion of each receipt once.. Email Msg: Dear Customer, GE Certified Repair Centre Pallavaram has received materials for repair / investigation. Kindly find the relevant details below... RECEIPT ID: RC51325 No OF BOXES : 2 MODE OF RECEIPT: COURIER NAME OF COURIER: BLUE DART DOCKET NUMBER: 68743541 We shall provide the next update upon unpacking, Physical verification of the materials. If you need further assistance, please contact <CRC Hotline> Thank you Certified Repair Centre | Completed | Receipt mail ID | Service.CRC@ge.com | Crc@12ge | Service.CRC@ge.com | Completed
2 | Pjysical Verification | Email has to be sent on Physical verification completion of all relays of a RMA once.. Email Msg: Dear Customer, Kindly find the Physical verification details of Receipt ID : <Receipt ID> below... RMA : <RMA> 1 RID: <RID> MODEL: <Model> SERIAL: <Serial> RECEIPT CONDITION: < PHYSICAL DAMAGE STATUS> Relay recived with the following (All relay received with status skipping not applicable criteria) 2. RID: <RID> MODEL: <Model> SERIAL: <Serial> RECEIPT CONDITION: < PHYSICAL DAMAGE STATUS> Relay recived with the following (All relay received with status skipping not applicable criteria) We shall provide the next update upon on (Warrantry / Chargable) declaration If you need further assistance, please contact <CRC Hotline> Thank you Certified Repair Centre | Completed | RMA email ID |  |  |  | Completed
3 | W/C Declaration | Email has to be sent on declaration completion of each relay Email Msg: Dear Customer, The below relay is declared to be repaired / Modified on <Warranty status> RMA : <RMA> RID: <RID> MODEL: <Model> SERIAL: <Serial> Defect reported by customer: <Defect> (Below line only for Warranty relay) (PCP conditions : W) The tentative date of dispatch would be <today +3 working days> (Below line only for chargable relay)(PCP condition: C) A quote containig Repair / Modification Charges would be updated you separately. If you need further assistance, please contact <CRC Hotline> Thank you Certified Repair Centre | Completed | RMA email ID |  |  |  | Completed
4 | Dispatch | Email has to be sent on dispatch of each DC Email Msg: Dear Customer, The below product shall be dispatched today with the below correspondance Delivery Challan: <DC> Courier Name : <Courier Name> Dispatch Docket : <Docket Number> 1. RMA : <RMA> RID: <RID> MODEL: <Model> SERIAL: <Serial> 2. RMA : <RMA> RID: <RID> MODEL: <Model> SERIAL: <Serial> If you need further assistance, please contact <CRC Hotline> Thank you Certified Repair Centre | Completed | RMA email ID | Alert for different RMA dispatch on selecting the RID |  |  | Completed
| RMA Site Card | Email has to be sent on Physical verification completion of all relays of a RMA once.. Email Msg: Dear Customer, We have received your request for repair and shall arrange modules/cards for this issues. RMA : <RMA> 1 RID: <RID> MODEL: <Model> SERIAL: <Serial> We shall provide the next update upon on (Warrantry / Chargable) declaration If you need further assistance, please contact <CRC Hotline> Thank you Certified Repair Centre | [5 empty] | Completed
| Email User ID | Forgot Password : no Mail ID - send mail to admin email ID. Mail ID available : send mail to particular ID password field to be removed in edit user | [5 empty] | Completed

## Query Report
Filters | Common details |  | Status
RID Serial No | Recipt No RMA no RID no Model No Serial No
Recipt Form | details | User ID/Date &Time | Completed
Form details
Status
Physical Verfication Form | details |  | Completed
Physical verification comment
Case (available/Conditon)
TB (available/Conditon) TB no
top/bottom Flop (available/Conditon)
Short Link available
Screws available
Sales Order
Status
RMA | Details | User ID/Date &Time | Completed
Description of fault/Modification
WBS/Sales Order
Cust. Inv & delivery Add
Status
W/C approval | Details | User ID/Date &Time | Completed
SMP /PCP(W/C)
Type
Move To
Comment
RCA tick Mail to details Message details
Status
Job Ticket | Details | User ID/Date &Time | Completed
Type of work
Repair Details
Power on test
Material Part No Qty Healthy PCB serial No Defective PCB serial No Individual PCB comment
Status
Testing | Details | User ID/Date &Time | Completed
Status ( Pass/Fail)
Comments
Ageing | details
Status ( Pass/Fail)
Comments
Verificatiion | Details | User ID/Date &Time | Completed
updated TB details ,Short link , SW version
Dispatch Approval | Details | User ID/Date &Time | Completed
Status ( Approved /Open )
Dispatch | Details | User ID/Date &Time | Completed
DC no
Disptach Method
Docket details
Courier Name
Status

## Receipt&RMA report
Combine Receipt and rma details in single report
Filter
Date | [9 empty] | Status
RMA no
Receipt No
List of Receipt Details | [9 empty] | Completed
All table content | User ID | Date & time
List of RMA detais | [9 empty] | Completed
RMA no | Model No | Serial No | Customer & end Customer Name | Customer Inv Address | Customer Delivery address | Physical Verirfication comment | Customer Comment | User ID | Date & time

## Dispatch report
Status
filter | Completed
Date
DC No
Cotent | Completed
show all dispatch details in table

## ZEBRA PRINTER connectivity issu
Notes | Status
Common page to add Ip address for RMA and Receipt print | Completed

## job ticket print
Change the heading and content fonts |  |  |  | Status
Change activity to notes |  |  |  | Completed
Table view
sl. No | Material no | Qty | Details
remove
test result documented
tested
completed date
Time spent

## verification print
Change page 2 check list to YES/NO | Status
Completed

## Dispatch Print
Notes
1. Details for packing Slip provided
2. Dimensions